## Sheet1
4.1 | Remove arcByCenterPoint and circleByCenterPoint from the list of geometric primitives in model of the feature catalogue. Also remove from the feature catalogue builder. Change also UML diagram as well as to the table 5-A-20. (JW).
4.2.1 | Include the metadata redline document, provided with proposal 4.2.1 into S-100 Edition 4 (JW).
4.2.2 | Further develop, and resubmit the proposal to add an integer attribute to S100_ProductSpecification. (EK, HB, DG, EM)
4.2.4 | Concerning metadata proposals (paper 4.2.4 items 2,3,4,5,6,8), an updated redline copy is to be forward to TSSO for inclusion in S-100 Edition 4. (EM, JW)
4.2.5 | Concerning the proposal to remove "Other" from S100_DataFormat, incorporatte the new language agreed during the meetin (??)
4.2.5 | Concider how to including S-100 complience levels - for inclusion in Edition 5 (???)
4.2.6 | Prepare redline exchange set and discovery metadata and forward to Chair for circulation. If agreed - forward to TSSO for inclusion in Edition 4 (EM)
4.3 | Include extra guidance on the interpolation method for bSline (for projection onto a spheroid) (hb)
4.3 | Request the DQWG to check quality aspect related to the dSpline issue.
4.3 | Include text to indicate that bSline should not be used for depth curves (or any other linear navigationally significant features).
4.3 | Define a common interpolation method for all geometries - to be proposed for Edition 5.
4.4 | GML clarification presented in 4.4 to be included Edition 4 (JW) ??
4.5.1 | Action: include the revise redline text (presented during the meeting) - for inclusion in Edition 4 (JW)
4.5.1 | Include the LUA proposal (paper 4.5.1) in Edition 4 as Part 9a (JW).
4.5.2 | Include the Scripting Language Extension (paper4.5.2) in Edition 4 as Part 13 (JW). (this will affect Part 0)
4.5.2 | SPAWAR to investigate how to implement a catalogues for alerts and indications (see old action) SPAWAR, HB, HP
4.7 | Include IALA proposal on online communication (paper 4.7.1) as Part 14 in Edition 4. (JW)
4.8 | Correct the attribute "featureUseType in Part 5 (JW)
4.9 | Action: include the proposal describing a standard method for encoding time in S-100 and dependent product specifications - for inclusion in Edition 4. (NCWG, HP, MH).
4.10 | Action: produce an updated version of the HDF5 proposal via correspondence group, circulate to WG for approval and, if accepted include as Part 10c - for Edition 4 Chair (???)
4.11 | update registry model for the Concept register (and other extension)(KHOA)
5.1 | report to HSSC the revised publication timeline
6.2 | Action: Invite appropriate Working Groups and Project Teams to appoint members to participate in the work of the GI Registry Project Team. (JW)
6.2.3 | Action: Inform HSSC10 meeting, about the activity to develop the Registry Guideline document (Annex A to S-99) as part of the S-100 report to the HSSC meeting. (Chair).
6.2.4 | Action: invite S-100 members to participate in the Sub WG to review the content of the Registry (IEHC, Canada, WMO)
6.4 | Action: include guidance on file naming conventions (based on paper 6.4) in the PS Guide book, taking into account the comments made during the meeting.
6.6 | Action: develop a generic set of validation tests that can be used as the basis for the development of Product Specifications. (BC, HB, US, IC-ENC, JW, Primar)
6.8 | Action: invite IEHG to harmonise their portrayal (colour tokens, style sheets and IE specific symbols) with those in the new registry. (DlaD)
6.8 | Action: include portrayal CSS’s in the registry and include explanatory text in S-99. (KHOA, JW)
6.9.2 | Action: submit paper 6.9.2 (Methodology for the display of quality information) to the S-101 PT meeting (June 2018) and the DQWG meeting (January2019).
6.10 | Action: submit paper 6.10 to the S-101PT (June) meeting for further consideration (SO).
6.10 | Action: investigate the extent of large numbers of data coverage’s within HOs ENCs – to report back to the June S-101 meeting. (IC-ENC, Primar, and other non RENC HO’s).
6.10 | Action: enquire whether the KHOA S-1xx datasets can be made available for testing (KHOA).
7.2 | S-100WG to review and comment on the first edition of the S-121 standard and to feedback comments in time for the documents to be updated prior to HSSC submission in May 2018
7.2 | Action: request a MLB domain for Maritime boundaries at the HSSC10 meeting. (Chair)
7.3 | Action: request a UKCPT domain for Under Keel Clearance at the HSSC10 meeting. (Chair)
7.4 | change the S-100 revision timeline for new editions to every 2 years (Chair)
8.3 | Change the catalogue filename for S-100 Edition 4. (Chair).
8.3 | Action send email to all WG PT developers to inform them that catalogue file will be called “catalogue.xml.”
8.3 | Action: include content about product catalogue structure in the guideline document.
8.5 | provide proposals on S-100 related recoendation for inclusion in S-100 Ed 4 redline (SPAWAR)
9.3.3 | Action: examine whether the draft checklist developed by IEC can be included in the S-100 Testbed documentation. (Chair)