## Sheet1
S-100 TSM7 Draft Actions
# | Chapter | Action | Who | Status
| 4.1 | Decision: it was agreed that the list in the recommendations presented in the peper would be used for testing as a starting point. |  | Decision
| 4.2 | Action: establish a sub-working group to produce a functional analysis of related products (from the mariner perspective) in order to define the operating principles governing S-100 ECDIS and to ensure that S-100 products and S-98 are consistent with the overall vision of the implementation strategy for S-100. |  | On-Going - need to ask for volunteers
| 4.3 | Action: report to the S-124CG that the TSM7 meeting considered that, when used in ECDIS S-124 data should be stacked as an overlay. [EM] | EM
| 4.5 | Action Circulate the items relating to Portrayal Harmonization in S-98 (TSM4.5) for wider review and comment, and present feedback to the S-100WG5. | EM / Chair | Complete - 5.1D
| 4.7 | Prepare a revised S-100 part to include the functional overview and use cases for S-98. | Chair | Complete - 5.1
| 5.1 | Develop a more comprehensive proposal on S-101 Display Scale for consideration at S-100WG5 | USA | OBE - Worked out an interpretation of S-101 that allows the US to compile to binary scales but set its display scale to S-101 values
| 5.2 | Action: Complete the alerts model and documentation for presentation, discussion and acceptance at S-100WG5. Check that all S-52 alarms and indications are included. Include a draft a “user story” showing the changes required to the Registry infrastructure. | NIWC | Complete - 4.4
| 5.2 | Action: investigate how to portray a safety depth contour from a navigational (S-102) coverage. What changes will be required in S-100? | ?? | Ongoing
| 5.2 | Action: Part 9 needs to be extended to derive a line from a coverage |  | Ongoing - who
| 5.2 | Action: include the mapping between the alert and the feature type. | Who? | Ongoing - who
| 5.2 | Action: Investigate what needs to be added to the portrayal catalogue builder to cater for building the alerts and indicator catalogue (a user story). [NIWC] | NIWC | Complete 4.4
| 5.4 | Decision: Need to check that all the alarms and indications that are currently included in S-52; are included in the xml scheme for the Alerts and Indications catalogue | S-101WG Chair
| 5.4 | Action: submit a proposal on how to close the capability gaps in the S-100 portrayal model (for discussion/acceptance at the S-100WG5 meeting) and for inclusion in S-100 Edition. | [NIWC, HB, HP] | Complete 4.11
| 5.4 | Action: Determine next actions for addressing dynamic portrayal and provide feedback on the recommended changes. |  | Ongoing - who
| 5.6 | Action: establish a small expert group to propose the necessary changes based on testing results presented in paper 5.6 (HDF5 inconsistencies) | HB, DG, DB
|  | Action: Input a comment sheet that includes the S-102 comment and propose the agreed changes as part of their input to the S-102 review - (review closing date 3 October). | HB, DB
| 5.7 | Action: Prepare change forms to implement Machine Readability of Display Plane Ordering and present to the next S-100 Working Group meeting. There should be one proposal for S-100 and one for S-98. | NIWC | Complete
| 5.8 | Action: prepare change proposal submission to implement the “S100_PR_ContextParameter” proposal for consideration at the S-100WG5 meeting [NIWC] | NIWC | Complete
| 5.9 | Action: Investing implementing the recommendations 1 to 4 in NIWC paper. For recomendations 2 and 3; submit change a change proposal for next meeting. Recomendations 1 and 4 may be proposed at a later time. | [T-Caris Seven seas, KHOA, NIWC]
| 5.11 | Proposed changes to S-100 Part 4a were accepted and are to be implented in S-100 Ed5 | TSSO
| 5.12 | Action: Submit a change proposal form for the proposed changes to the exchange catalogue structure. | [PRIMAR] | Complete
| 5.13 | Propose to replace the mechanism cancelling a datasets in the S-102 PS. To be done as part of the US comments on the IHO CL requesting review. | DB | Complete
| 5.13 | Action: Develop general guidance paper on how to managing dataset cancellation and dataset withdrawal for consideration at S-100WG5 and possible inclusion in S-100 Edition 5. |  | Complete
| 5.15 | Action: Submit a change proposal for the issues identified in paper TSM 5.15 (dealing with enhancements to S-100 Part 15) for consideration at the S-100WG5 meeting. (TSSO to provide Word version of S-100 Part 15 to Primar). | [Primar, IC-ENC, IIC-(JP)] | S-100 Part 15 Enhancements
| 5.16 | Full proposal on Signature and Certificate to be developed and submitted to S-100WG5 for inclusion in S-100 Edition 5.
| 5.17 | Action: Submit a change proposal for for the proposed amendments to HDF5 encoding as described in paper S-100TSM 5.17 (inclusion in S-100 Ed 5) | TWLWG | Complete?
| 5.19 | Action: Report the issues on the exchange set gaps to the full S-100WG with a view to forming a correspondence group to work on creating a new S-100 part. This is for S-100 Edition 6, and should include the proposals in paper TSM_5.19. It was agreed to get the minor proposals in paper 5.12 and 5.13 for inclusion in Edition 5.0.0 | [SS, EM, DG, RM, EK, KHOA, NOA NAVO, IC-ENC] | Complete
| 7.1A | Based on the meeting discussion on IMO performance standard, provide an updated version to D-Tech. | Chair | Complete