## WG VTC02_2021
S-100WG VTC02, 2021
Date updated: 9 January 2022
Meeting | Ref. Doc | No. | Subject | Actions | Responsibility | Status | Remarks
VTC02 | 3 | 2/01 | S-100 Part 2 | S-100WG members interested in participating in the Part2 Review Sub-Group to notify the IHO Sec.(Jeff) at their earliest convenience. IHO Sec (Jeff), NIWC (Dave), DK (Liz), ROK (Iji), IIC (Jonathan), NGA (Kevin), CCG (Eivind) joined the Sub-Group. | All | Completed
| 3 | 2/02 | S-100 Part 2 | The S-100 Part 2 Sub-Group submits the draft of S-100 Part 2 and S-99 at the next S-100WG for approval. | Vice-chair/ KHOA/ Sec | Completed
| 6 | 2/03 | HDF5 | BSH as a member of S-102PT, with collaboration of DQWG, to submit a proposal to S-100WG6 for approval. | BSH | Completed | Presentation RedLine Version WG6-4.5
| 7 | 2/04 | ItemIdentifier | The S-100 Part 2 Sub-Group to develop the remarks and submit the clarification of the sourceIdentifier in S-100 Part 5. | Vice-chair/ KHOA/ Sec
| 8 | 2/05 | Attribute chunking | BSH as a member of S-102PT to submit its proposal to S-100WG6 for approval. | BSH | Completed | Presentation RedLine Version WG6-4.4

## WG5_2020
S-100WG5 2020_Taunton
Date updated: 10 January 2022
Meeting | Ref. Doc | No. | Subject | Actions | Responsibility | Status | Remarks
WG5 | 4.1 | 5/01 |  | Members invited to support the work on developing the IALA guideline document on real time data / Web Services. This work should take into account the comments on the possible size of digital signatures, and the proposals in document 4.17. | IIC, IALA | Completed | Input given through this year and will be covered in Part 15 updat
| 4.2 | 5/02 |  | Advise the SCUFN Chair that the request for allocating product specification numbers must be submitted to the HSSC/IRCC | Chair | Completed
| 4.3 | 5/03 |  | Report back to Sintef thanking them for their paper, and inform them that the meeting considered their paper was more appropriat for the work being indertaken by the IEC (rout exchange format). | Chair/TSSO |  | TSSO: I have not communicated this - not sure if Julia did or not.
| 4.4 | 5/04 |  | The proposal for machine readability of display plane ordering (paper 4.4) was accepted for inclusion in S-100 Edition 5. This must include an update to the UML model (to include a new role). | Chair/TSSO | Completed
| 4.5 | 5/05 |  | Apply the proposed changes to the UML (Fig 9.10) and all other text changes to S-100 Part 9 – for Edition 5. | Chair/TSSO | Completed
| 4.6 | 5/06 |  | Implement the revised method of creating a reference between a feature catalogue and registry content. HB to provide KHOA with their comments on how to achieve this without having to implement the proposed changes. | HB/KHOA | Completed
| 4.7 | 5/07 |  | Amend the remarks and multiplicity (i.e. from 0:1 to 0:*) for the proposal on data replacement, and apply the other proposed editorial changes. (for inclusion in Edition 5). | PRIMAR/TSSO | Completed
| 4.7 | 5/08 |  | Develop guidance on managing dataset cancellation including dataset and ancillary file withdrawal proceedures. This task is to be included with the work that is to be done by the exchange set gap correspondence group (for inclusion in Edition 5). | PRIMAR/SEC |  | TSSO: Needs to be confirmed with PRIMAR. Am not aware of any feedback from the Exchange Set Gap CG(?).
| 4.8 | 5/09 |  | Develop a mechanism for documenting change control information for S-100 based product specifications. Ensure that all PS versions (including schemas and other associated resources) are available from the Registry - Prod Spec registers. (This needs to take account of paper 6.12.) | KHOA/TSSO | Closed
| 4.9 | 5/10 |  | Apply the proposal at Appendix 4a-D for attribute producingAgency. It was decided that this is to be dealt with by the metadata review group – (for Edition 5) Secetariat to send redline version of the original docment to SS. | SS/TSSO | Completed
| 4.9 | 5/11 |  | Include the revised proposal for S -100 Part 4 metadata, that was agreed by the meeting review group, (for Edition 5). (The redline document that includes the revised text, is to be sent to Secretariat). | SS/TSSO | Completed
| 4.1 | 5/12 |  | Apply all NIWC proposals in paper 4.10. (Note: these were also agreed at TSM7) (for Edition 5). | NIWC/TSSO | Completed
| 4.12 | 5/13 |  | Apply all NIWC updates to Part 9-7 “Data Input Schema” (for Edition 5). | TSSO | Completed
| 4.13 | 5/14 |  | Apply all proposed “Miscellaneous Revisions” updates in spreadsheet (for Edition 5) | TSSO | Completed
| 4.14 | 5/15 |  | pply the proposed changes for Part 10c (for the Edition 5) | TSSO/RM/HB | Completed
| 4.15 | 5/16 |  | Establish a validation sub group to develop validation checks that span across the entire S-100 framework. Target 2022 [t.b.d] | IC-ENC lead/IIC/Primar/HB/Chair | Completed | This sub-group has been established and has made good progress on developing checks for S-101, this work will support S-100 level checks. Due to S-101PT chair role volunteers to lead this group are sought from the WG. https://iho.int/uploads/user/Services%20and%20Standards/S-100WG/S-101PT7/S-101PT7_2021_08_EN_S-101%20Validation%20Checks%20Draft%200.1%2020210407.xlsx
| 4.16 | 5/17 |  | Add the compliance metadata extension proposed in paper 4.16 to Edition 5. Redline text to be finalised and submitted to TSSO for inclusion in Edition 5. | EM/TSSO | Closed | Redline was updated, but latest versions seems to be missing the explinatory text
| 4.17 | 5/18 |  | S-100 WG members invited to work with IALA to continue the devepment of generic S-100 data streaming specification – in conjunction with the OGC work. Report on the progress to be provided to TSM8 | IIC - lead | Completed
| 4.18 | 5/19 |  | Include the redline text for the new data Coding Format (proposed in paper 4.18), for S-100 Edition 5. | TSSO | Completed
| 4.2 | 5/20 |  | Proposal 4.20 on the HDF file famalies - to be take as correspondence for further discussion | Chair/Stacy
| 4.21 | 5/21 |  | The clarification relating to data offset code was approved - for Edition 5. Note; the name of the attribute name needs to be improved. | RM/TSSO | Completed
| 5.1 | 5/22 |  | Prepare a new redline version of S-98, that moves the abstract parts of S-98 into S-100 (part 16) and realign S-98 content so as to provide an interoperability implementation. The new part 16 will include the UML models and descriptive text on how to create an interoperability catalogue. Get approval from HSSC13. Provide the redline text to secretariat for inclusion in Edition 5. | Chair | Completed
| 6.2 | 5/23 |  | Invite MS and stakeholders to use the S-100 test bed platform for testing and verifying their test data. | Chair
| 6.2 | 5/24 |  | NIWC to forward the “user stories” study to KHOA and work with them to implement alerts and indicators into the Portrayal Catalogue Builder. | NIWC/KHOA | Closed | "user stories" PPT was submitted/presented, No direct feedback from KHOA.
| 6.4 | 5/25 |  | Post S-97 on the IHO website as Edition 1.1.0 | TSSO | Completed
| 6.7 | 5/26 |  | Metadata correspondence group to draft a new S-100 part for exchange and discovery metadata – for inclusion in S-100 Edition 5. | NOAA-lead/IIC/Primar/ICENC/Tel-CARIS | Completed
| 6.8 | 5/27 |  | Provide recommendation on the implementation of MRNs to the S-100 WG. Also include recommendation on what needs to be added in the Registry in order to make it usable at the database and product levels. | DL
| 6.9 | 5/28 |  | Provide a presentation/paper on the S-100 Open Online Platform to HSSC and recommend that HSSC invite MS, Industry and other experts to participate in the Open Online Platform project. | Chair/KHOA | Completed
| 6.12 | 5/29 |  | Invite DQWG to liaise with all other WG and PT’s that are developing product specifications (including from other organisations) in order to get feedback on what is required for testing environments, and what test assumptions should be included. | Chair
| 6.12 | 5/30 |  | Develop a “best practice” guidance document providing information on versioning and release management protocols for S-100. Investigate the possible development of and xslt tool to facilitate this. | HB/NIWC | Closed | "best practices" NIWC reported. No response back from Holger after sharing NIWC's versioning methods. Julia was going to check on NOAA "best practices" after his close-out.
| 6.12 | 5/31 |  | Noting the issues highlighted in paper 6.12 concerning Prod Spec feature catalogue inconsistencies, invite Netherlands to continue the development of the validation tool with a view to including it into the S-100 infrastructure tools. [NL, DQWG] | RB/DQWG | Closed
| 6.12 | 5/32 |  | Draft a straw man document on the technical and strategic process to be followed to ensure that product specification dependencies on S-100 Editions, are harmonised - for HSSC12. | Chair
| 7.2 | 5/33 |  | Inform the Assembly on the “dual-fuel” discussion/decisions and implications for the S-100WG. | SEC | Completed
| 7.3 | 5/34 |  | Submit a proposal to HSSC12 requesting that a new edition of S-64 (or other number), which includes a test regime and test datasets, be developed for S-100 ECDIS. | Chair | Completed
| 7.4 | 5/35 |  | Provide feedback to Australia on the discussion on temporal variation, and request that they submitted a revised version to the S-101PT and DQWG for consideration. | Chair/Aus
| 7.5 | 5/36 |  | Prepare a high level information paper that covers the principles of operation for the dual fuel concept. | IIC(lead)/Norway/ESRI/7Cs/NIWC/France/Finland/Canada/UK/Denmark/Sweden/Navtor/Primar/Italy/Netherlands/USA-NGA/NOAA/Furuno | Completed
| 8.1 | 5/37 |  | Work on the validation rules for S-102 data, that includes HDF 5 encoding. Start with checking the validation rules against the S-102 product specification. Prepare the next edition (of S-102) to meet readiness level 4. (for S-102 Edition 3 – 2023). | S-102 CG
| 8.1 | 5/38 |  | Request nomination for Chair / Vice chair of the S-102 PT. Nominations to be submitted to the S-100WG Chair. | Chair/Sec | Completed
| 8.1 | 5/39 |  | Submit propose to the next HSSC, informing that the publication Edition 5 of S-100, is requested be postponed untill early 2022. | Chair | Completed