## S-101PT Actions 20200907
S-101PT Actions @20200916
No. | Action | Detail | Lead | Status | Remarks
S-101PT4-01 | Finish the S-57 to S-101 Conversion Report | Incorporate comments received. Compile a list of edge cases from the UOC/DCEG part of the study. Release the test dataset containing a set of the edge cases for testing converter technology. | JP | Ongoing
S-101PT4-06 | NCWG activities affecting S-101 development | Draft amendments to the S-101 DCEG to make provision of encoding different colours of floodlighting. | JW | Ongoing.
S-101PT4-07 | NCWG activities affecting S-101 development | Consider how to reduce the triggering of “false” alarms in ECDIS through consistent encoding practices. This should be documented in the S-101 DCEG. | Chair/IHO Sec | Ongoing
S-101PT4-11 | DCEG Changes for S-101 Edition 2.0.0 | Discuss additional encoding guidance for the population of the depthRangeMinimum attribute for isolated shoal depth areas. | JW/AS/MH/RF | Ongoing
S-101PT4-14 | Sector Extension Portrayal Attribute | Improve the wording describing sector light extension as described in paper 5.5. | NIWC/JW | Ongoing
S-101PT4-15 | Sector Extension Portrayal Attribute | Conditional Symbology Procedure needs to be developed for item 2 in paper 5.5. | HA/HP/JW | Ongoing
S-101PT5-01 | Quality of Horizontal Measurement | Develop proposal for quality of horizontal measurement based on S-101PT4-5.4 discussion. | CM | New Action
S-101PT5-02 | Visualization of Quality of Bathymetric Data | Develop proposal for S-101PT consideration on possible amendments to S-101 modelling of the Quality of Bathymetric Data feature based on the outcome of the DQWG investigation of improved portrayal of this information in ECDIS (for TSM8). | JW | New Action
S-101PT5-03 | Visualization of Quality of Bathymetric Data | Consider the implementation of DQWG recommendations on improved portrayal of Quality of Bathymetric Data information in ECDIS (for S-101PT6). | S-101 Portrayal Sub-Group | New Action
S-101PT5-04 | Changes Intoduced in S-101 Edition 1.1.0 DCEG | PT members interested in participating in the S-101 DCEG Sub-Group to notify JW by email (jeff.wootton@iho.int) at the earliest opportunity. | S-101PT | Completed
S-101PT5-05 | Changes Intoduced in S-101 Edition 1.1.0 DCEG | Redline version of the S-101 DCEG to be sent to S-101 DCEG Sub-Group members for review (before end of September 2020). | JW | New Action
S-101PT5-06 | Changes Intoduced in S-101 Edition 1.1.0 DCEG | The definition as to what constitutes and “editorial” change to the S-101 DCEG is to be determined, in consultation with the S-101PT Executive (September 2020). | JW/Chair/Vice-Chair/YB | Ongoing | Email to S-101PT Executive 05/10/20.
S-101PT5-07 | Feature Catalogue | KHOA, Portolan Sciences (and any other interested parties) to review changes to the FC to ensure validitiy with S-100 FC schemas (As new versions of the FC are created). | KHOA/RM/HA/YB/NIWC | New Action | Email from Izzy 21/09/20. Note however that this action is intended to be ongoing.
S-101PT5-08 | Portrayal | PT members interested in participating in the S-101 Portrayal Sub-Group to notify the Vice Chair and JW by email (alvaro.sanchez@defence.gov.au and jeff.wootton@iho.int) at the earliest opportunity. | S-101PT | Completed
S-101PT5-09 | Portrayal | Engage with the S-100WG in regard to work required on S-101 portrayal, ECDIS performance, etc. (TSM8). | Vice-Chair | New Action
S-101PT5-10 | Validation Checks | PT members interested in participating in the S-100 Data Validation Sub-Group to notify the Chair and JW by email (thomas.richardson@ic-enc.org and jeff.wootton@iho.int) at the earliest opportunity. | S-101PT | Completed
S-101PT5-11 | S-101PT Work Plan | The draft S-101 Work Plan to be forwarded to the S-100WG Chair for S-100WG endorsement and inclusion in the S-100WG report to HSSC12; and to the IHO Secretariat for posting on the S-101PT page of the IHO web site (September 2020). | Chair | Completed | Included in S-100WG report (S-101PT Report) to HSSC12.
S-101PT5-12 | S-101PT Work Plan | Establish an Issues and Risk Log and design an S-101 Engagement Plan (S-101PT6). | Chair | New Action
S-101PT5-13 | Datum Issues | A small group, led by NIWC, to discuss the issues raised in the Paper S-101PT5-10. Possible feedback required to TSM8. | NIWC (Lead) | New Action
S-101PT5-14 | Navigational Purposes | A dedicated meeting of a small group to be convened to discuss the issues raised in Paper S-101PT5-11 (October 2020). Possible feedback required to TSM8. | NIWC (lead)/Chair/IHO Sec | New Action
S-101PT5-15 | VALSOU Decimal Places | Paper S-101PT5-12 to be considered by the DCEG Sub-group (November 2020). | S-101 DCEG Sub-Group | New Action
S-101PT5-16 | VALSOU Decimal Places | Paper S-101PT5-12 to be submitted to the ENCWG for consideration. | IC-ENC | New Action
S-101PT5-17 | Fairway Portrayal | Paper S-101PT5-14 to be considered by the Portrayal Sub-Group (November 2020). | S-101 Portrayal Sub-Group | New Action
S-101PT5-18 | Light Sector Portrayal | Paper S-101PT5-15 to be considered by the Portrayal Sub-Group (November 2020). | S-101 Portrayal Sub-Group | New Action
S-101PT5-19 | Quality of Bathymetric data and ECDIS Performance | Paper S-101PT5-16 to be considered by the Portrayal Sub-Group (November 2020). | S-101 Portrayal Sub-Group | New Action
S-101PT5-20 | Grouping of Soundings | Paper S-101PT5-17 to be considered by the Portrayal Sub-Group (November 2020). | S-101 Portrayal Sub-Group | New Action
S-101PT5-21 | Compendium of AHO Proposals | Paper S-101PT5-18 to be considered by the DCEG Sub-group (November 2020). | S-101 DCEG Sub-Group/S-101 Portrayal Sub-Group | New Action
S-101PT5-22 | S-57 to S-101 Encoding | Liaise with the S-100WG lead on S-57 to S-101 conversion (Jonathan Pritchard) on strategies that may be adopted for S-57 datasets to facilitate S-57 to S-101 conversion | S-101 DCEG Sub-Group | New Action
S-101PT5-23 | NIWC Testbed Update | DCEG Sub-Group to discuss the following issues raised in the NIWC Testbed Update report (S-101PT5-21 – listed by the associated Presentation slides): Slides 15, 21, 27. | S-101 DCEG Sub-Group | New Action
S-101PT5-24 | NIWC Testbed Update | Portrayal and ECDIS Performance Sub-Group to discuss the following issues raised in the NIWC Testbed Update report (S-101PT5-21 – listed by the associated Presentation slides): Slides 4, 12, 16, 17, 22, 25, 26, 28, 32, 33, 34, 35, 36, 37. | S-101 Portrayal Sub-Group | New Action
S-101PT5-25 | NIWC Testbed Update | NIWC to report to the S-100WG (TSM8) the following issues raised in the NIWC Testbed Update report (S-101PT5-21 – listed by the associated Presentation slides): Slides 15, 21, 27. | NIWC | New Action
S-101PT5-26 | NIWC Testbed Update | Paper to be developed to describe the implementation of units of measurement for weights and measures (in conformance to S-52 clause 10.8) (for S-101PT6). | Chair/RM | New Action
S-101PT5-27 | NIWC Testbed Update | National language support and ECDIS Pick Report issues (including those identified in slides 30 and 31 of the S-101PT5-21 agenda item presentation) to be addressed as a lower priority task (for S-101 Edition 1.x or 2.0). | S-101PT | New Action

## Completed_Closed
S-101PT Actions @20200916
Source | Action | Detail | Lead | Status | Remarks
S-101PT4 | Finish the S-57 to S-101 Conversion Report | Incorporate comments received. Compile a list of edge cases from the UOC/DCEG part of the study. Release the test dataset containing a set of the edge cases for testing converter technology. | Jonathan Pritchard | Complete
S-101PT4 | S-101 ENC Portrayal | Determine all portrayal gaps, Design portrayal on gaped features/types Sub-WG to work on refining the current symbols, line styles, sounding structure/portrayal, colours/palettes etc… . User feedback is to be sought as part of the work. | US/NOAA NCWG Chair [Members: IHO Sec, IALA, Carnival, Germany, Teledyne-Caris, IIC, NZ, KHOA, US (NOAA), US (NGA), Netherlands (DGWG Chair) | Complete
S-101PT4 | Update S-101 to final IHO GI Registry | Update content of S-101 for any changes based on IHO GI Registry deconfliction work | Jeff Wootton | Complete - all draft S-101 Edition 1.1.0 items aligned to the Registry.
S-101PT4 | Validation Checks | Denmark and IHO Sec to investigate incorporating the S-100 product validation checks into a database and developing a GUI interface. | Bruno Cardoso (DK) Tony Pharaoh (IHO Sec.) | CLOSED | Task OBE checks now fall within Validation Check Sub Group. New action to be taken. Agenda item 4.4 refers.
S-101PT4 | S-57 to S-101 Convertor | IHO Sec to include entries in the S-57 to S-101 conversion spreadsheet for new items included in S-101 Edition 1.0.0. | Jeff Wootton | Completed
S-101PT4 | S-57 to S-101 Portrayal Gap Analysis | Provide the spreadsheet identifying the new S-101 data modelling (refer action for Agenda item 4.4) to the NCWG Chair for consideration of the NCWG of new symbology requirements at its next meeting. | Jeff Wootton | Completed (August 2019)
S-101PT4 | Offshore Solar Farms | Netherlands to draft a definition for “solar farm” and submit to the Registry Manager (for registration). Registry Manager to include the new item in the DCEG. | AM/Jeff Wootton | Completed
S-101PT4 | DCEG Changes for S-101 Edition 2.0.0 | Continue application of draft changes to the S-101 DCEG in line with the changes approved by the S-101PT4 meeting and changes to the FCD Register. For further review at S-101PT5. | Jeff Wootton | Completed
S-101PT4 | Proposal of Alternate Options for Display Scale | Propose to the S-100WG Chair to include an item on loading strategy to be discussed at the next Test Strategy meeting. | Megan Bartlett (US) | Completed
S-101PT4 | Quality of Horizontal Measurement | Submit paper 5.4 identifying inconsistencies (with definitions) to the next DQWG. | Christian Mouden (FR) | Completed | See action S-101PT5-01.
S-100TSM7 | Visualization of Quality of Bathymetric Data | What extent does DQWG findings reflect in S-101? - Email Rogier and Yong | S-101PT | Completed | See action S-101PT5-02.
S-100TSM7 | Alerts and Indications | S-52 A&I needs to be captured in S-101 | US/NIWC | CLOSED | This is a Policy issue. There is no requirement for A&I in S-101, but there is a requirement in S-52.
S-100TSM7 | Alerts and Indications | Need to define what those mappings are (not all S-52 in S-101 and vice versa) | US/NIWC | CLOSED | Need to implement S-101 A&I in the PC using S-52 as guidance since there is nothing to guide in S-101. We are doing / have done the technical issue by adding A&I to S-101 PC.
S-100TSM7 | Alerts and Indications | Sumbit full proposal to S-100WG5 | US/NIWC | Completed