## S-101PT Issues Log
S-101 PT Issues Log - Items raised and not covered by a S-101 PT Action |  |  |  | Last Updated 20210128
Ref | Source | Title | Description | Way Ahead | Assigned | Ref
1 | Raphael Maylankar email 20200618 | Portrayal viewing groups and display priorities, documentation | RM seeks confirmation of the priorities to be used in S-101 and asks whether a document defining the viewing groups will be provided. | Port SG to consider generating a listing as part of S-101 1.1.0 | Port SG | N/A
2 | NIWC Email 20200625 | Various S-52 Requirements Gaps | Areas where current standard doesn’t support achieving S-52 requirements need to be resolved. | Portrayal SG to consider items raised by Testbed reports. | Port SG | S-101PT5-21
3 | RM Email 20200624 | Text placement | KHOA have updated FCB, reported at PT5. | Review updated FC in due course. | KHOA | N/A
4 | RM email 20200701 | Context parameters and the Registry |  | Portrayal SG to consider. | Port SG
5 | DAYMAR Display | Base/Standard? |  | Assigned to Portrayal Sub Group. | Port SG | N/A
6 | Offensive terms | Offensive terms to be removed entirely from S-101. | Affects DCEG table 2.7 only as named associations supersede. | Assigned to JW to resolve through DCEG sub group to be resolved in draft for PT review early 2021. | JW | ENCWGXX
7 | S-101PT5-21 | Units of Measure in the S-101 Feature Catalogue | Current S-101 FC does not hold UOM which is required for pick report. Actions to review where UOM codelist is held and ensure FCB supports inclusion in FC. Then add in S-101 FC. Add clariying guidance in S-100. Also consider attriubute constraints and quantity specification. | Information paper for S-101PT 6 and paper to TSM8 in March to resolve. | TR | S-101PT5-21 Slide 29
8 | NGSM, NIWC | Presentation of Non-HO Data | Not currently covered in Portrayal Catalogue or S-101. | Passed to Portrayal SG. | Port SG | Email discussion