## Sheet1
S-101 Portrayal and ECDIS Performance Requirements log
Req. # | Date of registration | STATUS | Approved at | Documents | Short Description | Areas of development |  |  | Modelled ? | Tested? |  | Comments | Final Decision
[6 empty] | Feature Catalogue | Portrayal Catalogue | OEM - ECDIS |  | Test Bed | Mariners Input
1 | 2020-10-20 | Withdrawn |  | S101PT5 -16 | Automated downgrading of QoBD using new proposed attributes: categoryOfQobd (or CATZOC); temporalValidity; lowestQobdCategory and downgradeQobd. | Yes | Yes | ????? | Not Possible (reported by NIWC) | N/A | N/A | Refer to Github Issue # 4. | Recommend S-101PT accept and implement NIWC's proposal and WITHDRAW this Requirement.
A new proposal from NIWC recommends adding only one new (complex) feature attribute to QoBD (fixedDateRange) and encode multiple QoBD features (using same geometry and sequential date ranges) to directly influence and control the transitions between categories of QoBD. Additional encoding guidance should be included in DCEG.
2 | 2020-12-09 | Pending | S101PT6 | NCWG3-08.4A S101PT5-21 | New portrayal options fro category of QoBD (screen wide & ship centered options). | No | Yes | Yes | No | No | No | Refer to Github Issue # 7.
[5 empty] | New ECDIS performance - Safety function - Include category of QoBD as a trigger for Alarms/Warnings during Route planning and route monitoring. | No | Yes | Yes ? | No | No | No
3 | 2020-12-09 | Pending | S101PT6 | DQWG-05.1B S101PT5 -13 | QoBD - Visualization of Vertical and Horizontal Position uncertainties | Yes | Yes | Yes ? | No | No | No | Refer to Github Issue # 1.
4 | 2020-12-09 | Pending | S101PT6 | S101PT5-17 | Standardisation of the 'Review Update' function in ECDIS. Include ability to, during route check planning face, highlight and report 'ENC update changes' applied since last review. | No | Yes | Yes | No | No | No | Refer to Github Issue # 5. Endorsed by S101PT6
5 | 2021-06-29 | Pending | TBS | Unknown yet | Implementation of standardised MSVS that 'align with' (tabulated value + 1) DCEG 2.5.9 Table 6 entries. | No | No | Yes | No? | No? | No | Informally discussed at various S101PT meetings. Potential paper to be presented by SHOM at S101PT7 (Nov 2021). Refer to email trail from CM on 26/6/21.
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21

## Sheet2
Pending
Testing Underway
Approved
Not Approved
Withdrawn