## Sheet1
S-101 portrayal subWG - Github Issues status |  |  |  | Decisions and Actions |  |  |  |  | Updated status at NOV2021 (2nd subWG meeting) | S101PT Action #
Issue No | Topic | Summary of comments received | Recommended actions for S101PT6 approval | Decision | Action | # | Who | Status
1 | Quality of Bathymetric Data - Visualization of Vertical and Positional Uncertainties | In general terms, the comments received supported the development and testing of portrayal and ECDIS's in-built safety functions in support of the encoding of positional and depth uncertainities for critical hydrographic features in line with the paper presented by the AHO and the DQWG (also note HSSC12 endorsement of DQWG recommendations). Due to limitations regarding DF-ECDIS performance, it's recommended that the implementation (if supported by testing and mariners feedback) of this new functionality is deferred to a post S-57 sunset date. Development and testing should start sooner than later though. | Postpone implementation to post DF-ECDIS date QoBD remodelling dependent (DCEG subWG) | Postpone implementation to post DF-ECDIS date | Add requirement to 'S-101 ECDIS Performance' log | 1 | AS | Completed | Added to ‘S-100 ECDIS Performance requirements log’ (as future development considering it will be difficult to be accepted in DF-ECDIS). At 2nd subWG meeting, it was decided to create a dedicated Github issue for each entry in the log in order to continue discussions including the appropiate implementtaion timeline (DF-ECDIS or not). It was noted that S-101 test datasets are required to progress development and testing. Norway volunteered to produce them. New actions (43, 44)
|  |  | 1) Approve the use of Horizontal Position Uncertainty & Vertical Uncertainty to affect portrayal and ECDIS performance as described in the papers available in Github. | Horizontal Position Uncertainty & Vertical Uncertainty are to affect portrayal and ECDIS performance as described in the papers available in Github. | Develop a portrayal proposal capable of managing both, positional and depth uncertainty values on charted Sounding, Underwater Rock, Wreck and Obstruction | 2 | KHOA AS | Completed |  | PortSG-01
[5 empty] | Develop changes to the A&I catalogue and on-shore ECDIS to implement the use of Horizontal Position Uncertainty, Vertical Uncertainty and displayUncertainties by ECDIS in-built route checking safety functions. Use the 'ECDIS expected performance' section of paper DQWG15_2020_05.1B as an starting point for this job. | 3 | NIWC | Completed |  | PortSG-02
[5 empty] | Create new Github issues for each entry in the 'ECDIS Portrayal and Performance log'. | 43 | AS | Pending | New action created (see above) | TBA
[5 empty] | Produce S-101 test datasets as required to support development and testing of actions # 2 & 3. | 44 | Norway | Pending | New action created (see above) | TBA
|  |  | 2) Approve adding a new boolean attribute (uncertaintyDisplay Yes/No) to QoBD to control the display of uncertainties indicators in ECDIS to the following feature types: Sounding, Underwater Rock, Wreck and Obstruction. In order to support development and testing, this change should be included in the next version of the FC. | Add new boolean attribute displayUncertainties to the following feature types: Sounding, Underwater Rock, Wreck and Obstruction. | Update DCEG | 4 | JW | Completed | DCEG & FC 1.0.1 | PortSG-03
[5 empty] | Update FC | 5 | JW/KHOA | Completed
|  |  | 3) Seek KHOA's support for the development of a portrayal proposal capable of managing both, positional and depth uncertainty values on charted Sounding, Underwater Rock, Wreck and Obstruction features. | Approve recommendation. Refer to Action # 2.
|  |  | 4) Seek NIWC's suport to assess the requirements needed to implement the use of Horizontal Position Uncertainty, Vertical Uncertainty and uncertaintyDisplay into future S100 ECDIS in-built route checking safety functions (in line with the content of the 'ECDIS expected performance' section of paper DQWG15_2020_05.1B ). This may include but not be limited to changes to the A&I catalogue, on-shore ECDIS, etc. The integration of the new portrayal and safety functions will require thorough testing and mariners'input before final approval. | Approve recommendation. Refer to Action # 3.
2 | Fairway portrayal | Norway has provided S101 sample data to NIWC and NIWC has generated and shared, ECDIS dsiplay images (Day and Night modes) to compare existing grey colour depiction of Fairways against the preferred new option supported by the subWG which is faint magenta. This Issue is awaiting Norways feedback (as the proposer of the change). Once Norway approves the new colour, they will have to formalise the change request using the newly introduced online 'Portrayal request form'. Once received by Alvaro, it will be managed in accordance with the new 'Portrayal request workflow'. | Note the progress on this Issue. | Await fromal proposal by Norway. | Submit full proosal using the online ''S-101 Portrayal request from'. | 6 | Norway | Completed | A 'minimalistic' proposal (DF-ECDIS compatible) was explored and supported by this subWG and the NCWG but it did not fulfill Norway's expectations and therefore it was abandoned (decision has been recorded in Github). Norway wil prepare and submit a different proposal that may or may not be accepted for implementation in DF-ECDIS. New Action (45) | PortSG-04
[5 empty] | Prepare new portrayal Fairway proposal without the constraints DF-ECDIS may impose to the proposed solution. | 45 | Norway | Pending | New action created (see above) | TBA
3 | Light Sector Portrayal - Sector Light Length | The group was able to come up with a 'mapping table' that supports all the different ECDIS selector options vs relevant attribute values for both S-52 and S-101. Norway has requested access to an updated test version of the S101 PC (NIWC to provide) to visualise the proposed SLL behaviour in real case scenarios. Norway would then report back to the group on their test results, lessons learnt and recommendations. All these to be discussed at a later stage. | Note the progress on this Issue. | Await Norway's testing and feedback. | Provide updated version of the PC to Norway | 7 | NIWC | Completed |  | PortSG-05
[5 empty] | Report lessons learnt and/or submit full proposal to S-101PT7 | 8 | Norway | On Hold | 1. - Issue passed to the DCEG subWG for further discussions. Particularly around the expected behaviour when ECDIS setting 'Full sectors'' is turned ON/OFF. Consideration must be given to impact on mariners'experience when using DF-ECDIS (SLL is not available in S-57). 2.- It was also agreed that a Validation test should be developped to check that SLL <= valueOfNominalRange 3. - It was agreed that ECDIS performance requierements should be expanded to mandate the ability to display light sector arms and arcs when the position of the light is outside the display area. In the same circumstances, pick-report must detect and report light sectors characteristics. New Actions (46, 47, 48) | PortSG-06
|  |  |  | Discuss amendments to DCEG to improve guidance on the use of this attribute. | Coordinate discussions within DCEG subWG and report back recommended changes to PC to the portrayal subWG. | 46 | JW | Pending | New action created (see above) | TBA
|  |  |  | Recommend new Validation test | Pass recommendation for a new validation test that checks SLL <= valueOfNominalRange to S-101 Validation subWG | 47 | AS | Pending | New action created (see above) | TBA
|  |  |  | Initiate actions to guarantee recommended ECDIS performance when lights sit outside the display area. | Add requirement to 'S-101 ECDIS Portrayal and Performance' log and create dedicated Github issue. Also submit change request to S-98 Part C. | 48 | AS | Pending | New action created (see above) | TBA
4 | Quality of Bathymetric Data and ECDIS Performance (Management of Temporal variation) | In general terms, the comments received supported the retention of the QoBD feature attribure categoryOf TemporalVariation and the addition of a new integer attribute temporalValidity. Although the proposal to implement a new functionality in ECDIS to auto-downgrade QoBD was not supported it was highlighted that the addition of the complex attribute fixedDateRange would be highly beneficial as it could support the encoding and simultaneous release of a number of different QoBD objects that would be turned off/on by ECDIS like any other 'temporal objects' as the time goes by. This encoding guidance should be included in the DCEG as a possible option for HO's to manage areas 'likely to change' that may not be re-surveyed at the pace they should. Other HOs may simply decide to use temporalValidity in the first and only published QoBD feature and let the mariner discover and calculate (based on survey date range - survey end) its 'due by' date via pick report. | QoBD remodelling dependent (DCEG subWG)
|  |  | 1) Retain categoryOfTemporalVariation as a valid QoBD feature attribute. | Approve recommendation. | Nil
|  |  | 2) Approve adding fixedDateRange complex attribute to QoBD to facilitate a 'user controlled' downgrading of QoBD. | Allocate discussion and remodelling to DCEG subWG | DCEG subWG to discuss and present to the S101PT re-modelliing proposals in support of the temporal downgrading of QoBD. | 9 | JW | Completed | Changes made in version 1.0.1 but S-101 test datasets are required to perform testing and analysis. New Action (49) | PortSG-07
2) Approve adding a new integer attribute (temporalValidity) to QoBD to express the expected duration of the published quality of the bathymetry in an area. This would provide useful information to mariners when categoryOfTemporalVariation is encoded as 'likely to change' (2,3). The encoding of temporalValidity is not to be mandatory but, if populated, the encoding of survey date range - survey end with a meaningul value (not Unknown) should be mandatory.
|  |  |  | S-101 Test data is requiered to complete this task. | Compile S-101 ENC using FC 1.0.1 | 49 | TBA | Pending | New action created (see above) | TBA
5 | Grouping of Soundings in ENC Updates | Very limited input and not against the recommendations made in the original proposal. These proposals are therefore considered as accepted by this subWG and directly passed to S101PT6 for endorsement. NIWC will update their on-shore ECDIS to support testing and provide more insights. | 1) Add the standardisation of the ‘Review Update’ functionality in ECDIS to the newly proposed S-101 ECDIS performance log for further develoment and testing. Any proposed solution must include mariners input and therefore it's recommendd that a survey form is prepared and distributed to key stakeholder forums (TBD) to gather their views. The pracfical use of the UpdateInformation feature as well as the impact of grouping new/modifed soundings into existing groups and/or deleting features that were part of an existing sndg cluster would have to be thouroghly tested. | Approve recommendation. | Add requirement to 'S-101 ECDIS Performance' log | 10 | AS | Completed | At 2nd subWG meeting, it was decided to create a dedicated Github issue for each entry in the log in order to continue discussions including the appropiate implementtaion timeline (DF-ECDIS or not). Refer to Action # 43
|  |  | 2) In the meantime, it's proposed to include guidance in the DCEG recommending encoders not to include new/modified soudings into existing sounding groups when creating an ENC Update. This encoding guidance should be passed to the ENCWG for consideration. | Approve recommendation. | Add guidance in new version of the DCEG | 11 | JW | Underway | Planned for version 1.0.2 | PortSG-08
[5 empty] | Inform the ENCWG chair so this guidance can be considered for inclusion in the UOC. | 12 | JW | Underway | Noted by Jeff. He will follow up on this issue with ENCWG Chair. | PortSG-09
|  |  |  | S-101 Test data is requiered to support this task. | Compile S-101 ENC and ENC Update that add, remove, modify Soundings. | 50 | TBA | Pending | New action created (see above) | TBA
6 | Portrayal Catalogue 1.1.1_1.n.n Endorsement and update to registry | No input in Github. Refer to Portrayal subWG VTC meeting Issue # 6 actions. After comment from JW it has been decided to align the FC version to the next PC version (1.0.1 not 1.1.1). | 1) The IHO Secretariat to create a new Github repository to formally manage the review and approval of NIWC's PC versions underpinning testing and development. The S101PT is asked to recognise and endorse that NIWC's PC versions approved in Github will be used as the source to generate any official IHO S-101 PC version. | Approve recommendation. | Already captured and tracked as S-101PT6-07.
|  |  | 2) NIWC is to upload their latets PC version to Github and seek feedback in order to obtain formal aproval for version 1.0.1. The S101PT is requested to determine a due by revision date. |  | Upload latest draft of the PC to the new Github repository. Any futher changes to be timely reflected and tracked in this location. | 13 | NIWC | Completed |  | PortSG-10
|  |  | 3) Once Github approval is obtained, the IHO Secretariat, (asssited by KHOA), would generate the corresponding official S101 PC 1.0.1 versions and would update the IHO GI Registry. |  | Publish 'official' PC version 1.0.1 (in line with FC and DCEG 1.0.1) | 14 | IHO Secretariat KHOA | Pending | Various discussions regarding version management and branching within Github. Focused discussions between keystakeholders required in order to progress this task. New Action (51) | PortSG-11
|  |  |  | Focused meeting among key stakeholders required | Organise VTC meeting to discuss PC versioning and best practices regading the use of terms such as 'official'or 'master' versions. | 51 | AS, JW, TR, NIWC | Pending | New action created (see above) | TBA
7 | Quality of Bathymetric Data - Decide portrayal requirements | In general terms, the comments received support the retention of the existing CATZOC symbology in the short term (DF-ECDIS) and the addition of a new feature atribute categoryOfZoneOfConfidence (or simlar) to the existing QoBD modelling. This would simplify portrayal rules (Rogier to validate mapping rules) and would retain terminology that is currently in use and is well understood by mariners (now also well documented in S-67). There was also consensus regarding the need for a more holistic approach for the display and integration into ECDIS safety functions of the quality of bathymetric data information (future symbolization of QoBD in S-100 ECDIS). | QoBD remodelling dependent (DCEG subWG)
|  |  | 1) Endorse the retention of the existing S-52 CATZOC symbology as S-101 QoBD symbology during the DF-ECDIS period. | Approve recommendation. | Update PC draft as required | 15 | NIWC | Pending | NIWC - Please confirm status | PortSG-12
|  |  | 2) Endorse the addition to of a new feature attribute categoryOfZoneOfConfidence (or simlar) to the current QoBD modelling. | Approve recommendation. | DCEG subWG to update QoBD modelling as required | 16 | JW | Completed | version 1.0.1 | PortSG-13
|  |  | 3) Endorse the addition of a new work item to the 'S-101 ECDIS Performance' log regarding the development and testing of new ECDIS functionalities and visualization methods linked to the final modelling of QoBD. This work will require extensive mariner's engagement, testing and the implementation of a comprenhensive communication strategy aimed to introduce and educate users on the new ECDIS performance and/or display standards (to commence at least 1 year before the end of S-57 & S-52). | Approve recommendation. | Add requirement to 'S-101 ECDIS Performance' log | 17 | AS | Completed | At 2nd subWG meeting, it was decided to create a dedicated Github issue for each entry in the log in order to continue discussions including the appropiate implementtaion timeline (DF-ECDIS or not). Refer to Action # 43
8 | Portrayal of shared edges | A way forward has been suggested by CARIS and accepted in principle by NIWC. NIWC will develop, test and report results back to the PT. | Note the progress on this Issue. | Await NIWC's input. | Test proposed solution and report back to S-101PT7 | 18 | NIWC | Underway | NIWC to implement instructions to supress identical edge symbology for simple line styles (same feature types only) AND to allocate new 'combined symbology (TBD)" to AnchoraAreas (only feature for now). A 'combined' complex linestyle for adjoining AnchorageArea features needs to be developped to support testing.(after meeeting Github input by NIWC - dash & symbol patterns can be aligned in post processing with no change to portrayal. This can be done while evaluating line suppression. - sub group to recommend/mandate this practice via S-98 change proposal). New Actions (52, 53) Maybe delete both and replace with action to submit change proposal to S-98 | PortSG-14
|  |  |  | Proceed with testing of improved symbolosation instructios regarding shared edges between adjoining QoBD features and also between adjoining AnchorageArea features. | Develop anchorage area 'combined' complex linestyle for testing. | 52 | KHOA | Pending | New action created (see above) | TBA
[5 empty] | Amend portrayal instructions to use new complex linestyle symbology when two adjoining AnchorageArea features adjoin and share and edge. Report findings. | 53 | NIWC | Pending | New action created (see above) | TBA
9 | Id values in portrayal catalogues | A decision has been made to update S-101 PC using xmlID but the registry does not currently show a value for xmlID. | 1) Endorse the decision and task the IHO Secretariat to add xmlID values to the registry. | Approve recommendation. | Add xmlID values to the registry | 19 | JW | On Hold | Discussions around the name of the acronym and its description of use in S100 Part 2. Suggestions were made to review this. As a first step JW will organise a meeting with , JB and KHOA to discuss thhis topic further (particularly in regards to IHO Registry) and will brief AS, NIWC, Holger and Hugh to come up with best way forward which could include a proposal to amend S100 Part 2. New Action (54) | PortSG-15
[5 empty] | Update PC with xmlID values | 20 | NIWC | On Hold |  | PortSG-16
|  |  |  | Put previous actions (19, 20) on hold until more information is gathered from KHOA's development team. | Discuss xmlid with KHOA's development team in order to get a better understanding of its format and its use within the IHO Registry database. Once more information is gathered, further discuss best way forward with key stakeholders. | 54 | JW, JB, KHOA (first) JW, DG, AS, HB, HA (second) | Pending | New action created (see above) | TBA
10 | Light descriptions with unknown lightCharacteristic | It seems that the preferred option is to build the light's description as per the existing guidance in S-52 10.6.3 and skip (do not display) rythmOfLight when this feature attribute has not been encoded or it has been encoded as 'unknown'. It has been noted that S-98 Annex C C-14.10.4 has the same table than S-52 (updated to S-101) but adds that: "Values not listed in this table are not represented in the light description string." | 1) Endorse the interpretation of the subWG. | Endorse the interpretation made by the subWG | Update PC to support the interpretation endorsed by the S101PT | 21 | NIWC | Completed
11 | Guidance for the implementation of 'temporary' overlays | After discussions NIWC has decided that no further actionis required. This issue will be closed in Github. | Note the decision on this issue. | Support subWG decision | Close issue in Github | 22 | AS | Completed | Implemented in 'Master'PC version managed in IHO's Github | PortSG-17
12 | S-101 PC and Mariners viewing groups | Very limited input but it seems that the way forward would be removing mariner's viewing groups/ viewing group layers from S-101 PC and ensuring any associated requirements in this space get well documented in S-98 Annex C. Mariners symbols and viewing groups should be managed and implemented by OEMs. | 1) Endorse the removal of mariner's viewing groups/ viewing group layers from S-101 PC. | Endorse the removal of mariner's viewing groups/ viewing group layers from S-101 PC | Remove mariner's viewing groups/ viewing group layers from S-101 PC | 23 | NIWC | Completed | Mariners groups have been removed from the PC | PortSG-18
|  |  | 2) Confirm S-98 Annex C contains enough detail as to support the implementation of this requirement. | Support way forward. | Liaise with S-100WG Chair and IEC T80 representative to resolve this issue outside the S-101 PC | 24 | NIWC | Pending | NIWC - Please confirm status, including notification to S100WG to update S-98 with guidance for OEMs | PortSG-19
13 | SY(CHDATD01) symbol has no portrayal parameters | Very limited input but enough as to support the implementation of a viewing group layer for CHDATD01 only. There's no support to also include the viewing groups for INFORM01 (31030 and 31031). | 1) Endorse the implementation of a new viewing group layer for CHDATD01 only. | Endorse recommendation | Portrayal Register - Add new Viewing Group Layer to manage the independent selection (on/off) of SY(CHDATD01) | 25 | JW | Completed | Decision to use the same portrayal context parameters than the 'I' symbol and allocate a new Viewing Group. New Action (55) | PortSG-20
[5 empty] | Implement changes to on-shore ECDIS | 26 | NIWC | On Hold | Awaiting allocation of Viewing Group number (see below) | PortSG-21
|  |  |  | Use the same portrayal context parameters than the 'i' symbol and allocate a new Viewing Group | Allocate new Viewing Group, seek S101PT approval and commence process to be included in the IHO Registry. | 55 | AS | Underway | Proposed Viewing Group is 31032 - If approved by S101PT, JW to update Registry and NIWC to update on-shore ECDIS | TBA
14 | Guidance on Date dependent and Safety check | Very limited input as to make a decision. The idea is to identify if the current wording in S-52 is too open and therefore lead to an undeisred interpretation/implementation by some OEMs. The overall intention is to avoid this in S-98 Annex C. NIWC is seeking details about current implementation practices by Furuno and SevenCs. | Note the progress on this Issue. | Await NIWC's input. | Report back to S-101PT7. Note that S-64 3.0.0 expanded the test data for this purpose. | 27 | NIWC | Completed | Agreed current S-52 guidance does not gurantee standardised implementation by OEMs. Also, an indication similar to the one required in S-52 Part I (10.4.1) for Route Monitoring should be expanded to Roue Planning and alert mariners when performing 'route check'using today's date. It was decide to close this issue at the Portrayal subWG level and pass S-98 Part C amendment proposal to S100WG. New Action (56) | PortSG-22
|  |  |  | Close issue and pass recommendations regading amendments to S-98 Part C to S100WG. | Submit S-98 Part C change proposal recommending more clear direction on the implementaion by OEMs, of mariners'selected dates and Route checking functions at both, route monitoring and route planning phases. | 56 | NIWC, AS | Pending | New action created (see above) | TBA
15 | IEC 61174 (4.18) Default selector requirement | Based on the feedback from NIWC, Furuno and SevenCs, the undesratnding is that S-52 text groups are independent of the display mode. | 1) Inform the ENCWG Chair of the interpreation made by NIWC, SevenCs and Furuno regarding the practical implementation of the relationship between text groups and display modes and highlight the conflict it creates with the S-52 statement indicating that text is in IMO display category "Other". | Endorse recommendation | Inform the ENCWG chair | 28 | TR (Chair) | Pending | TR - Please confirm status (Not discussed @ the 2nd Portral subWG meeting) | PortSG-23
|  |  | 2) Recommend the S-100WG remove statements from S-98 indicating text is in "Other". | Endorse recommendation | Propose S-98 amendment to S-100WG chair | 29 | TR (Chair) | Pending | TR - Please confirm status (Not discussed @ the 2nd Portral subWG meeting) | PortSG-24
|  |  | 3) Support the update of the S-101 Portrayal Catalogue so that viewing group layers associated with text are not included in any catalogued display mode (i.e. remove viewing group layers "Important Text" and "Other Text" from display mode "Other". | Endorse recommendation | Update PC and on-shore ECDIS as required | 30 | NIWC | Completed | PC has been updated so that viewing group layers controlling text are not included in any catalogued display mode (e.g. text groups are not in base, std, or other) | PortSG-25
16 | OEM guidance on application of changes to viewing groups | Very limited input and needs broader consultation before making any decisions. This topic seems to impact more than just S-101 and may need to be scalated to the S100WG for inclusion in S-98 Annec C. | 1) Discuss the extent of this Issue and recommend NIWC to submit paper to S100WG (update to S-98). | Escalate issue to S100WG | Submit paper to S100WG recommending update to S-98 Annex C | 31 | NIWC | Pending | Github issue has been closed - NIWC - Please confirm this has been escalated to the S100WG | PortSG-26
17 | S-101 Feature dependency issues | Discussion is still underway. NIWC has started identifying features that can negatively affect display if they are not turned on/ff simultaneously. They will be also looking at implementation strategies to regulate the selective viewing of features. Their findings and proposals would be presented to the subWG for comments and a way forward. NIWC plans to submit an S-100 change proposal for TSM8 / S-100WG6 which supports these changes. The change is to the Parent instruction in S-100 Part 9a - it adds a featureID parameter. | Note the progress on this Issue. | Await NIWC's input. NIWC provided comments in Github on 13/4/21. They have decided to close this issue, therefore no further action ids required. | Submit change proposal to TSM8/S100WG6 recommending update to S-100 Part 9a | 32 | NIWC | Cancelled
18 | Independent Mariner Selections | No input yet. NIWC will prototype implementation and then seek feedback from OEMs and the rest of the subWG. | Note the progress on this Issue. | Await NIWC's feedback. | Report back to S-101PT7 | 33 | NIWC | Pending | Discussions around the importance of pushing the 'machine readability'concept as much as possible in S100. It was clear that in order to achieve this, existing guidance should be made requirements. This lead to the questions 'where is the line'and 'who decides where the line is". It was decided that the topic needs further focused discussions at another level as it will need to be considered in the DF-ECDIS Governance document and it will require changes to S101 PS and S-98. New Action (57) | PortSG-28
|  |  |  | Facilitate a workshop to discuss the implementation of independent mariners selections in DF-ECDIS and beyond. | NIWC to chair workshop and prepare draft Agenda and proposed dates. S-101PT Chair to submit the invitation to OEMs and S100WG. | 57 | TR, DG | Pending | New action created (see above) | TBA
19 | ENCWG 'ENC Display subWG' | The lead of the ENC Display sub WG will liaise with the ENCWG and recommend/organise the migration of their findings to the S-101PT using the online S-101 Portrayal change request form. The ENC Display subWG would be disbanded once this task is completed. | Note the progress on this Issue. | Endorse way forward. | Submit portrayal change proposals identified by the ENC display subWG to the S101PT using the online 'S-101 Portrayal request form' | 34 | CM | Cancelled | Change of plan. CM will assess all existing 'ENC display subWG' entries with a small group of volunteers first. Those display requierements that do apply to S-101 will be included as new issues in the S101 Portrayal subWG Github space. Replaced with New Action (58) | PortSG-29
|  |  |  | Relevant ENCWG display issues will be included in the S101 Portrayal subWG Github space for discussions instead of preparing formal portrayal change proposals and submitting them through more formal channels. | ENC display subWG lead to seek volunteers and organise a focused meeting to identify valid S101 portrayal proposals and create Github issues for each of them in the S101 Portrayal subWG space. | 58 | CM | Pending | New action created (see above) | TBA
20 | ECDIS Chart 1 | The general consensus was that an S-101 ECDIS Chart1 is required and to pass the question about othe product specific 'ECDIS Chart 1' to the S100WG. At this point in time it seems they should be considered optional. | 1) Approve the creation of and maintenance of an S-101 ECDIS Chart 1 draft version. | Endorse recommendations.
|  |  | 2) Seek volunteer to develop the first version. |  | Seek volunteers (or HSSC funding) to develop the first 'S-101 ECDIS Chart 1' (or ECDIS Chart S101) version as per the requirements listed in S-52 Ed 6.1.1 (3.1.4) and S-52 PL Part I (17.7 & 18.2) | 35 | TR (Chair) | Pending | TR - Please confirm status | PortSG-30
|  |  | 3) Inform the S100WG Chair of this decision and the S101PT view in regards to other S-100 product specific 'ECDIS Chart 1' datasets. |  | Inform decision and way forward to S100WG Chair | 36 | TR (Chair) | Pending | TR - Please confirm status | PortSG-31
21 | S101 ECDIS Performance requirements log | A better understanding of what items may not fit within the new S-98 Annex C would be beneficial (await feedback from its review process). The AHO will prepare and maintain an S-101 ECDIS performance requirements log to keep records of new functionalities approved by the PT that cannot be implemented in a DF-ECDIS scenario and need further development and testing in preparation for a 'pure' S-100 ECDIS era. Some requirements may be possible to manage within the IHO realm (e.g. catalogues, etc) but others may need to be implemented by OEMs. These requirements will have to be properly documented and included in the corresponding ECDIS type approval document. | Note the progress on this Issue. | Endorse the creation of the 'S-101 ECDIS performance requirements' log. | Create, update and present S-101 ECDIS performance requirements' log prototype to S101PT7 | 37 | AS | Underway | Log created under the premise that entries wouldn't be supported for DF-ECDIS or that the level of development and testing required wouldn't allow us to finish it in time for S101 2.0.0 (they are enhancements not core requirements anyway). Despite this, the subWG at its 2nd VTC meeting decided to create Github issues for each of them and try to move them forward as if they would be acceptable/ready for DF-ECDIS. This particular topic reinforced the need for clear guidance on who has the power to clear a portrayal/alarms&indications variations between S-52 and S101 for DF-ECDIS use. Refer to New Action (43) and cretae New Action (59). | PortSG-32
|  |  |  | Decide on who has the authority to approve amendments to S-101 portrayal/alarms&Indications that conflict with S-52. | Submit request to S100WG Chair (decision must represent IHO Sec. view). | 59 | TR | Pending | New action created (see above) | TBA
22 | Portrayal proposals - Workflow and Form | The 'Portrayal update request form' has been aligned with the one used in the IHO's Registry. KHOA has expressed their willingnes to assist with the development of draft SVG files in support of any portrayal proposals, members or other IHO WGs, decide to put forward for consideration. | Note the progress on this Issue. | Note the progress and thank KHOA for their support. | Close Issue in Github | 38 | AS | Completed
23 | Review new portrayal requirements related to S-101 new/remodelled features and attributes | The spreadsheet created by TSSO has been uploaded to Microsoft365 and Alvaro and Jeff are reviewing the remodelled and new entries that could have impact on portrayal. Their findings and recommended portrayal change requirements would be presented to the subWG for endorsement. Once consesus is reached, new portrayal (symbols, rules, etc) would be developped and tested with NIWC's and KHOA's asssitance. | 1) Note the progress on this issue | Noted.
|  |  | 2) Recommend best way forward for final approval of symbology/rules. | Final approval allocated to the portrayal subWG. | Finalise review by 04APR2021; seek portrayal subWG approval and liaise with NIWC and KHOA as required to update PC as required. Report progress to S101PT7 | 40 | AS | Underway | Due to low participation the review period was extended to 02Jul2021. Decisions were made based on majority of votes (when possible) or, when more contentious, dedictaed Github issues were created to continue the discusions in a more focused way. KHOA, NIWC and others have been notified of decisions that require their support. Refer to 'Remodelled spreadsheet_FINAL Actions_17NOV2021' that has been uploaded to the Documents section of the Github space. This document includes dedicated columns to track progress of the new actions (106) and to document the subWG view regarding the recommended timing of their implementation (DF-ECDIS or after). The S101PT is asked to endorse the decisions/actions outlined in the latest version of the spreadsheet. Once endorsed, changes to rules and symbols in the S-101 PC 'Development' version are to be processed although the DF-ECDIS question must be cleared by NNN (??) before changes are passed to the 'Approved' S-101 PC version. | PortSG-37
|  |  | 3) Seek KHOA's support to develop new draft SVG symbology when required. Draft symbology would follow new 'Portrayal workflow'. | Agree but exclude Mariners' input.
|  |  | 4) Seek NIWC's support to implement new or update existing rules. | Agree.
26 | Light Sector portrayal - Sector arc extension | New Issue added after the Portrayal subWG VTC meeting. NIWC has outlined a possible way forward but they need our input. Requires more input from the subWG. | Note the progress on this Issue. | Seek more input from subWG. | Continue discussions in Github and report final recommendation at S101PT7 | 39 | AS | Completed | It has been agreed that sector arcs must extend with SLL and that 'double arcs'are not required. Note this issue is linked to SLL discussions in Github issue #3. Complete this issue and create New Action (60) | PortSG-33
|  |  |  | Sector arcs must extend with SLL and 'double arcs' are not required. | Irrespective of SLL behaviour (still under discussion in DCEG subWG), implement sector arcs behaviour decisions in PC. | 60 | NIWC | Pending | New action created (see above) | TBA
27 | Duplicate - see Issue # 23
28 | Small Craft moorings - Update symbology | New Issue added after S-101PT6 | N/A | Create issue in Github. | Report progress at S101PT7 | 41 | AS | Underway | Github issue created and continues open awaiting input on symbolistaion alternatives. | PortSG-35
29 | flipBearing attribute for TextPlacement | New Issue added after S-101PT6 | N/A | Create issue in Github. | Report progress at S101PT7 | 42 | AS | Completed | Github issue created. flipBearing concept accepted. It was aldo decided that it will work with centred justification and therefore the need to use textJustification was no longer needed. DCEG subWG will follow up on these two items and further discuss the possibility of expanding texttype values. The possibility of rotating text at an angle to avoid clashing with other text/features when reading at comp. scale and north-up was considered out of scope and it won't be pursued unless a apper is submitted to the S101PT. Memebers highlighted that the succesfull implementation of flipBearing will require ENC production tools that allow manual 'on the screen' text positioning (e.g. dragging and dropping the text visually while the software populates bearing and distance in the background). New Action (61) | PortSG-36
|  |  |  | Pass changes to DCEG and further discussions on this topic to DCEG subWG | DCEG subWG to make changes to DCEG. | 61 | JW | Pending | New action created (see above) | TBA
30 | Default text position when textPlacement is not encoded |  |  | No additional requierements reagding 'default' text positioning are needed. Instructions have been succesfullly migrated from S-52. | Close Issue. | 62 | AS | Completed
31 | Restricted Area Navigable vs Restricted Area Regulatory |  |  | HIGH Priority - Seek resources to produce ad-hoc S-101 native test data as required. | Bring topic to the S101PT to escalate as required (Volunteers or use Special Projects Fund) | 63 | AS | Pending | Agreement that the reason for splitting Restricted Areas was for alarms and indications purposes. It was noted that using CSP RESARE04 in S-101 Restricted Areas can produce a different end result when the same features are displayed from an S-57 or S-101 ENC. Differences seem to be minor and therefore they could be accepted in DF-ECDIS. Despite this initial assesssment, thorough testing using all CSP combinations in both standards should be carried out before a final decision is made (New action 63, 64). It was also decided to remove Restricted Area Regulatory from a 'branch' of the A&I catalogue (New Action 65) and to allocate this feature to a new Viewing group to be created (New Action 66). | TBA
|  |  |  | Create test data to support decision making process | * NIWC to, in a 'branch' of the S101 PC, add RESARE04 to Restricted Area Regulatory to support testing. * Create test data that contains all possible CSP RESARE04 attribute combinations. Compare portrayal results using S-52 and S101 PC. | 64 | NIWC, TBD | Pending |  | TBA
|  |  |  | Create A&I catalogue version to support testing. | Remove Restricted Area Regulatory from a 'branch'of the A & I catalogue. Pending confirmation this action will not break any IMO regulation. If approved to proceed, it will require changes to S-98 Part C (14.9.8) regarding the 'Detection of areas for which special conditions exist'. | 65 | NIWC | On Hold
|  |  |  | Register new Viewing Group | Allocate and register new Viewing Group for Restricted Area Regulatory. Remove this feature from current VG. | 66 | AS, NIWC | Pending |  | TBA
32 | Masking of edges by portrayal rules |  |  | Needs more work by the DCEG subWG | DCEG subWG to review section 2.5.10 and narrow them down to thojse not currently poerformed by ENC production tools. | 67 | JW | Pending | Decided that DCEG subWG should review existing recommendations in section 2.5.10 of the DCEG and narrow them down to only those that are not handled by ENC Production systems (New Action 67). They should focus on describing scenarios that require manual intervention. This review process may end up identifying things that could be handled by portrayal rules. Those issues could be sent back to this subWG for discussion. | TBA
33 | New symbology - Rapids |  |  | Discuss topic with Canada and Russia | Email summary of discussions and ask for preferred way forward (accept removal of Point as an allowable geometric primitive or submit proposal for new symbology). | 68 | AS | Pending | Only 2 countries use Point geometry for rapids; Canada and Russia. General agreement that Point should be removed as allowable geometric primitive but Canada and Russia should be engaged and asked to either support this decisions (noting alternative encoding guidance would be removed from DCEG) or submit new portrayal proposal to S101PT. (New Action 68). | TBA
34 | Display of the seaward edge of mangrove in intertidal areas |  |  | Pass remodelling proposal to DCEG subWG | Request the DCEG subWG to discuss discontinuing categoryOfVegetation = 7 & 21 and expand categoryOfObstruction to include 'mangroves'. | 69 | JW | Pending | Discussions around the intention behind the change. This was two fold, firstly to get the seward edge as a grey dashed line but also acknowledge that mangrove areas 'in the water' are dangers to navigation and therefore they should be part of Base display and trigger an indication during route monitoring and planning. The subWG decided to make changes to the modelling and proposed to pass this issue to the DCEG subWG to investigate the use of Obstruction and categoryOfObstruction instead of using Vegetation and categoryOfVegetation (New Action 69). | TBA
35 | Limitations in display of Sloping Ground |  |  | Leave issue open to continue discussions regarding best way of symbolising these features (by CATSLO or by CONRAD ?). | Update Github issue and leave open for further discussions | 70 | AS | Underway | Initially, and based on Github commnets,the subWG accepted to symbolise non radar conspicuous categoryOfSlopingGround values 1 (cutting), 2 (embankment), 3 (dune) and 4 (Hill) as per 6 (Cliff). This is using AC(CHGRD). After some discussions it was agreed that a better option would be to have two different symbologies (irrespective of CATSLO) to simply differentiate bewteen radar and non radar conspicuos features. This would require the development of new symbology for non-radar conspicuous SlopingGround features (New Action 70). Irrespective of the way forward on this, it was decided to discontinue the use of categoryOfSlopingGround= 5 & 7 (New Action 71). | N/A
|  |  |  | Update FC and DCEG | Remove categoryOfSlopingGround= 5 & 7 from list of valid attribute values. | 71 | JW | Pending |  | TBA
36
36 | Current non-gravitational |  |  | Update FC and DCEG | Remove Curve and Surface from the list of valid geometric primitives for this feature. | 72 | JW | Pending | to use waterwayDistance and | TBA
37 | Virtual Aids to Navigation |  |  | Seek more input from key stakeholders | IALA and CSMART representtaives to discuss the topic more broadly with their organisatiosna and present proposal via Github. | 73 | Antonio, Gottorm | Pending | The use of variations of the existing IEC symbols was discussed and no agreement was reached. Same with the use of text acronyms to support the types of V-AIS. The subWG decided to ask representatives from IALA and CSMART to discuss the topic more braoadly within their communities and report back via Github. Note that in the men time KHOA has been tasked to create SVG symbols using existing S-52 drawing instructions (New Action 73). | TBA
38 | Signal generation |  |  | Add (man) when signalGeneration=3, 5, or 6 (by hand, radio activated, or call activated) | Update LightFlareAndDescription rule to add (man) when signalGeneration=3, 5, or 6 (by hand, radio activated, or call activated). For FogSignals , add "(man)" next to the symbol (FOGSIG01). | 74 | NIWC | Pending | The subWG approved proposal in Github. Add text "(man)" at the end of the light description. At the meeting'it was decided to expand criteria to include 'by hand' (New Action 74). Recommend including new abbreviation to S-98 Annex C (Table 36) (New Action 75). | TBA
|  |  |  | Include new abbreviation 'man' in S-98 Annex C (Table 36). | Submit change proposal to S100WG | 75 | AS | Pending |  | TBA
39 | Measured distance value |  |  | Create and register in the IHO Registry (IHO Hydro domain) DISMAR05 symbol variation. | Develop new SVG symbol (DISMAR06?) identical to DISMAR05 but in CHMGD colour. Submit registration request to IHO Registry manager. | 77 | KHOA, AS | Pending | It was generally agreed to display distanceUnitOfMeasurement and waterwayDistance (e.g. km15) next to the distance mark location using the text style and size currently used by InlandENCs. (but in CHMGD colour). For distance marks on physical structures, portrayal would only display the previously mentioned text as the location will be 'covered' by the structure object itself. For distance marks 'not physically installed' the plan is to use DISMAR05 (InlandENC symbol) but in CHMGD colour and the previoiusly mentioned text next to them (New Action 76, 77). There were discussions about changes to the modelling of DistanceMark, particularly when associated to a physical structure (to be discussed by the DCEG subWG) (New Action 78). DISMAR03 and DISMAR04 would be discontinued (New Action 79). Units of measurement currently without an abbreviation must have them included in S-98 Annex C (New Action 80). | TBA
|  |  |  | Update DistanceMark rule | Update rule to display text string made of distanceUnitOfMeasurement followed by waterwayDistance. Same style than the one used in InlandENCs but in CHMGD colour. | 77 | KHOA, AS | Pending |  | TBA
|  |  |  | DCEG subWG to continue discussion about DistanceMark modelling options. | Discuss options around the best encoding practice for DistanceMark on physical structures (e.g. 2 associated features or complex attribute on each possible supporting structure ?). Also consider new bolean attribute (displayDistance?) for measuredDistanceValue to have control of the textual display on screen. Distance marks 'not physicaly installed' would be the only ones encoded using the feature DistanceMark. In this case the recommendation would be to have a new dedicated VG for this feature. This way both, the symbol (magenta circel) and the text would be turn On/Off simultaneously. The circle without the text does not make sense to me - all ON or all OFF). | 78 | JW | Pending |  | TBA
|  |  |  | Discontinue DISMAR03 and DISMAR04 SVG symbols | Remove from S101 PC and amend status in IHO Registry | 79 | NIWC, JW | Pending |  | TBA
|  |  |  | Include abrreviations for Statute miles and Yards in S-98 Annex C (Table 36). | Submit change proposal to S100WG | 80 | AS | Pending |  | TBA
40 | Air Draft'as a context parameter to trigger alerts in ECDIS |  |  | Await outcome of the paper at S101PT meeting and keep the Github issue open to continue discussions. | N/A |  |  | On Hold | The subWG supported the intent of the UKHO paper and agreed that additional context parameters, based on other ship dimmensions, could be introduced and used alike the one in the proposal. The general view is that ECDIS performance should be as standardised as possible and that changes to the Portrayal and Alarms & Indications catalogues can assist with this goal. It's expected that any new ECDIS performance requirements will be included in the 'S101 Portrayal and ECDIS Performance' log as a placeholder for development and testing in consultation with OEMs.
[7 empty] | Completed | 22
[7 empty] | Pending | 43
[7 empty] | Underway | 8
[7 empty] | On Hold | 6
[7 empty] | Cancelled | 2
81

## Sheet2
Pending
Underway
Completed
On Hold
Cancelled

## Sheet3
The subWG approved proposal in Github. Add text "(man)" at the end of the light description. At the meeting'it was decided to expand criteria to include 'by hand' (New Action 74). Recommend including new abbreviation to S-98 Annex C (Table 36) (New Action 75).
1. - Issue passed to the DCEG subWG for further discussions. Particularly around the expected behaviour when ECDIS setting 'Full sectors'' is turned ON/OFF. Consideration must be given to impact on mariners'experience when using DF-ECDIS (SLL is not available in S-57). 2.- It was also agreed that a Validation test should be developped to check that SLL <= valueOfNominalRange 3. - It was agreed that ECDIS performance requierements should be expanded to mandate the ability to display light sector arms and arcs when the position of the light is outside the display area. In the same circumstances, pick-report must detect and report light sectors characteristics. New Actions (46, 47, 48)
Submit S-98 Part C change proposal recommending more clear direction on the implementaion by OEMs, of mariners'selected dates and Route checking functions at both, route monitoring and route planning phases.
Include abrreviations for Statute miles and Yards in S-98 Annex C (Table 36).