## Feuil1
|  |  |  | LONGER TERM PLAN |  |  | TRLS levels requirements
Work item | Required product specification component | Status on 2020-10-28 (v2.0.0 October2019) | Comments | March 2021 (S-100 v4.0.0) | March 2022 (S-100 v4.0.0) *Requirement: TRL4 | March 2023 (S-100 v5.0.0) | (TRL5) Level 1 v1.0.0 | (TRL6) Level2 v2.0.0 | (TRL7) Level 3 >v2.0.0 | (TRL8) Level 4 >v2.0.0 | (TRL9) Level 5 >v2.0.0
A1 | Develop Edition 3.0.0 of S-102 Bathymetric Content Specification |  |  |  |  | S-102 v3.0 (LEVEL4+)
A1.1 | Main Document (Defines the relevant parts of S-100 that are required for the product specification) | Complete |  |  |  |  | x | x | x | X | x
A1.2 | A Default Encoding | Complete |  |  |  |  | x | x | x | X | x
A1.3 | S-100 Compliant Feature Catalogue | Partially complete | This will subdivide later with more details from PT | S-102 v2.1 (LEVEL3) | S-102 v2.2 (LEVEL4) | S-102 v3.0 (LEVEL4+) | x | x | x | X | x
A1.4 | DCEG (Data Classification and Encoding Guide) | Partially complete | This will subdivide later with more details from PT | S-102 v2.1 (LEVEL3) | S-102 v2.2 (LEVEL4) | S-102 v3.0 (LEVEL4+) | x | x | x | X | x
A1.5 | S-100 Compliant Portrayal Catalogue | Partially complete | This will subdivide later with more details from PT. This should be determined as part of the development process and stakeholder feedback | S-102 v2.1 (LEVEL3) | S-102 v2.2 (LEVEL4) | S-102 v3.0 (LEVEL4+) |  | x | x | X | x
A1.6 | Data Quality Checks | Partially complete | This will subdivide further with more details from PT. We need to better understand what is existing now. We need more information of what has been done in the past and define guidelines we need to send to the DQWG. | S-102 v2.1 (LEVEL3) | S-102 v2.2 (LEVEL4) | S-102 v3.0 (LEVEL4+) |  | x | x | X | x
A1.7 | Test Data Sets | Partially complete | This will subdivider further with more discussion from PT. We need to know if we need variety of dataset for different situations (ex.: different source of data LIDAR, MBES, Crownsource etc.) | S-102 v2.1 (LEVEL3) | S-102 v2.2 (LEVEL4) | S-102 v3.0 (LEVEL4+) |  | x | x | X | x
A1.8 | Data Validation (and test datasets) | Partially complete | This will subdivide later with more details from PT. We need more information of what has been done in the past and define guidelines we need to send to the DQWG/or other IHOsub group? | S-102 v2.1 (LEVEL3) | S-102 v2.2 (LEVEL4) | S-102 v3.0 (LEVEL4+) |  | x | x | X | x
A1.9 | Exchange Catalogue | Partially complete | This will subdivide later with more discussion from PT. Is it more S-57, S-101 related? | S-102 v2.1 (LEVEL3) | S-102 v2.2 (LEVEL4) | S-102 v3.0 (LEVEL4+) |  | x | x | X | x
A1.10 | Encryption / Digital Signatures (S-63) | Partially complete | We need more information of what has been done in the past and define the guidelines we need to send to the right WG. | S-102 v2.1 (LEVEL3) | S-102 v2.2 (LEVEL4) | S-102 v3.0 (LEVEL4+) |  |  | x | X | x
A1.11 | Interoperability (S-98, S-101, S-104) | Not included | S-98 is still being developed. |  | S-102 v2.2 (LEVEL4) | S-102 v3.0 (LEVEL4+) |  |  |  | X | x
A1.12 | Alerts and Indications | Not included | This component is not yet present in S-100. |  | S-102 v2.2 (LEVEL4) | S-102 v3.0 (LEVEL4+) |  |  |  | X | x
A1.13 | Operational data | Not included |  |  |  | S-102 v3.0 (LEVEL4+) |  |  |  |  | x
Color legend
Complete
Partially complete - In progress
Not included
Objectives: (See A1.11 and TRL8-Level4) | i) Develop the S-102 Product Specification to S-100 Readiness Level 4
i) Ensure that S-102 is designed for interoperability within the S-98 framework and specifically with S-101 Electronic Navigational Charts and S-104 Water Levels