## Sheet1
Status of Acrions from S-100 Working Group Test Strategy Meeting 6 Busan, ROK (September 18-20th) Actions
| Section | Action | Who | Status
1 | 4.1 | Submit a paper to the 4th S-100WG meeting outlining the issues relating to dataset compression. | RS, DG
2 | 4.2 | Submit the MRN paper and proposals to the IALA e-nav and NIPWG meetings for their consideration and comments. Feedback to be sent to EM. | EM
3 | 4.4 | Revise the model for alerts taking into account the TSM6 discussion (i.e. constrain the model to dataset alerts and use the portrayal model for triggering alerts). | (DG/HP) | Complete TSM7-5.2
4 | 4.4 | Set up a review group to consider what other "alert and indicator" type use cases are required for other product specifications. There is s need to determine what additional requirements are needed (e.g. what spatial operators should to be taken into account). | DG, BS, HA, HP
5 | 4.5 | Address the items raised in the paper 4.5 (Binding Specific Concepts) at the Registry workshop to take place in conjunction with the S-100WG4 meeting. | JW
6 | 4.7 | Provide a demonstration of the new Registry application at the Registry workshop (preceding the S-100WG4 meeting). | YB
7 | 4.1 | Include information on the S-100 site about the approval process for Edition 1.0.0 Product Specifications. | TP
8 | 5.2 | Circulate the S-98 draft document for S-100WG comment after the DQWG feedback has been incorporated. Consider moving the PS template in S-100 Part 11 into the S-98 document. | Chair
9 | 6.3 | Form a correspondence group (led by SPAWAR) to resolve the (text display) issues in recommendation 4 | [DG, EK, HA, HB, HP, EM] | OBE TSM7-5.4
10 | 6.3 | Implement the changes presented in paper S-100WG2-8.9 items 6-7 in S-101. Chair to remind the S-101PT of the issue presented in the paper. | Chair
11 | 6.3 | Submit change proposal form for recommendations 5 to 11 for consideration by the S-101PT. | SPAWAR
12 | 6.3 | Submit an change proposal for the issues identified in recommendation 13 relating to the need for a new interpolation method. | SPAWAR | Ongoing TSM7-5.3b
13 | 6.3 | Submit a change proposal form for recommendations 14 and 15. | SPAWAR | Ongoing 14: TSM7-5.3b 15: S-100WG4-4.8 (complete)
14 | 6.3 | Revisit the test bed report for consideration by the S-101PT i.e. for the issue relating to recommendation 16. | SPAWAR | Completed
15 | 6.3 | Form a correspondence group to study the issues indentified in recomendation 17, and submit proposal for consideration at the next S-100WG meeting. | [EK,EM,HB, HA,HP DG …]
16 | 6.3 | Write a paper outlining the issues in recommendation 18 and proposing a way forward | EM
17 |  | submit a proposal to the S-101PT highlighting the issues identified in recommendation 20 relating to turning on / off viewing groups.
18 | 6.3 | Submit an information paper to NCWG reminding the WG of the requirments to complete the task relating to the S-101 symbols (see recommendation 21). | Chair
19 | 6.3 | Write an information paper with recommendations on how to move the items described in recommendation 22 forward. | NOAA
20 | 6.3 | Sort out a central location were all catalogue files will be location for download. | Chair, IHO Sec
21 | 7.9 | S-124PT to request HSSC to agree on the split in scopes of the current S-412 PS into additional PS’s and request additional S numbers for the two additional PS’s. | JoeP

## My Notes
Status of Acrions from S-100 Working Group Test Strategy Meeting 6 Busan, ROK (September 18-20th) Actions
| Section | Action | Who | Status
1 | 4.1 | Submit a paper to the 4th S-100WG meeting outlining the issues relating to dataset compression. | RS, DG | S101 data protection proposal (Primar) | Paper on data complression
2 | 4.2 | Submit the MRN paper and proposals to the IALA e-nav and NIPWG meetings for their consideration and comments. Feedback to be sent to EM. | EM
3 | 4.4 | Revise the model for alerts taking into account the TSM6 discussion (i.e. constrain the model to dataset alerts and use the portrayal model for triggering alerts). | (DG/HP) | Complete TSM7-5.2
4 | 4.4 | Set up a review group to consider what other "alert and indicator" type use cases are required for other product specifications. There is s need to determine what additional requirements are needed (e.g. what spatial operators should to be taken into account). | DG, BS, HA, HP
5 | 4.5 | Address the items raised in the paper 4.5 (Binding Specific Concepts) at the Registry workshop to take place in conjunction with the S-100WG4 meeting. | JW
6 | 4.7 | Provide a demonstration of the new Registry application at the Registry workshop (preceding the S-100WG4 meeting). | YB
7 | 4.1 | Include information on the S-100 site about the approval process for Edition 1.0.0 Product Specifications. | TP
8 | 5.2 | Circulate the S-98 draft document for S-100WG comment after the DQWG feedback has been incorporated. Consider moving the PS template in S-100 Part 11 into the S-98 document. | Chair
9 | 6.3 | Form a correspondence group (led by SPAWAR) to resolve the (text display) issues in recommendation 4 | [DG, EK, HA, HB, HP, EM] | OBE TSM7-5.4
10 | 6.3 | Implement the changes presented in paper S-100WG2-8.9 items 6-7 in S-101. Chair to remind the S-101PT of the issue presented in the paper. | Chair
11 | 6.3 | Submit change proposal form for recommendations 5 to 11 for consideration by the S-101PT. | SPAWAR
12 | 6.3 | Submit an change proposal for the issues identified in recommendation 13 relating to the need for a new interpolation method. | SPAWAR | Ongoing TSM7-5.3b
13 | 6.3 | Submit a change proposal form for recommendations 14 and 15. | SPAWAR | Ongoing 14: TSM7-5.3b 15: S-100WG4-4.8 (complete)
14 | 6.3 | Revisit the test bed report for consideration by the S-101PT i.e. for the issue relating to recommendation 16. | SPAWAR | Completed
15 | 6.3 | Form a correspondence group to study the issues indentified in recomendation 17, and submit proposal for consideration at the next S-100WG meeting. | [EK,EM,HB, HA,HP DG …]
16 | 6.3 | Write a paper outlining the issues in recommendation 18 and proposing a way forward | EM
17 |  | submit a proposal to the S-101PT highlighting the issues identified in recommendation 20 relating to turning on / off viewing groups.
18 | 6.3 | Submit an information paper to NCWG reminding the WG of the requirments to complete the task relating to the S-101 symbols (see recommendation 21). | Chair
19 | 6.3 | Write an information paper with recommendations on how to move the items described in recommendation 22 forward. | NOAA
20 | 6.3 | Sort out a central location were all catalogue files will be location for download. | Chair, IHO Sec
21 | 7.9 | S-124PT to request HSSC to agree on the split in scopes of the current S-412 PS into additional PS’s and request additional S numbers for the two additional PS’s. | JoeP